## List
Item | Description | Phase | DFMEA | Check | Reference Document | Reference Document
1 | Information of component should be updated in following sheet. | Strategy Review |  | Not Applicable
2 | USB should be with IF certification, with TID#, for MFI certification. | Strategy Review |  | Not Applicable
3 | Package solution, mounting solution and layout pattern: reviewed and confirmed with PE and PCBA layout team before requiring GPN. PS: If SMT connector is with Nylon, package should follow standard requirement. | Strategy Review |  | Checked
4 | If connector is used for cable, following items should be received and defined in Garmin drawing. -crimping specification, -crimp dimensions, like CW …, -pull force, -manufacture guideline | Strategy Review |  | Not Applicable
5 | EOL risk evaluation, any EOL plan or guaranteed product life? | Strategy Review |  | Checked
6 | CADStar library creation: | Strategy Review |  | Checked
7 | Drawing release: before lab build | Strategy Review |  | Checked
8 | Can material pass SMT reflow? If specification cannot pass SMT reflow, sample should be provided to PE for test? | Detail Design | 23 | Not Applicable
9 | Once the new connector drawing is released, common use connector table should be updated for including. | Strategy Review |  | Checked
10 | Review key dimension and feature of 3D and 2D drawing and confirm if they match real part | Strategy Review |  | Checked
11 | Disassemble one sample or inspection by X-ray for studying structure before strategy review (only for USB, AUX, HDMI, SD) | Strategy Review |  | Not Applicable
12 | Strategy review and mitigation plan in strategy review | Strategy Review |  | Checked
13 | SD slot should be with stop feature for preventing card is miss-insert to clearance between opening and connector. | Detail Design | 27 | Not Applicable
14 | Confirm how to inspect spring height to avoid plug in/out failure(e.g. force, electical pin contact…) | Detail Design |  | Not Applicable
15 | If connector need to be mounted by MPS, PCBA design should follow MPS rule. | Detail Design |  | Checked |  | MPS S:\AutoOEM\07_Work rule\MPS Rule
16 | Mounting design, risk and quality should be reviewed in lab build. Review result should be updated in lab build close meeting report. | Lab build |  | Not Check
17 | Pass bending test | Lab build |  | Not Check | Follow the NDS to complete the (F=78N) | Front IO: ENG072: 5.8.8 S:\AutoOEM\07_Work rule mail: RE Bending test for front IO connector of Asian AOEM unit Rear IO: TBD
18 | FAI completed: by factory prototype build | Factory Prototype Build |  | Not Check
19 | Once FAI process is done, common use connector table should be updated for defining where use. | Factory Prototype Build |  | Not Check
20 | Mounting solution, risk and reliability should be reviewed by factory prototype build. Review result should be updated in factory prototype close meeting report | Factory Prototype Build |  | Not Check